## Slide 1
Task 2a: Mesocosm instruments/infrastructure
Peter Regier, Emma Cotter
mCDR AOP monthly update: February
Long-term Goals
Develop a continuous monitoring sensor package of CO2 dynamics for diverse mesocosm and coastal system applications
Approach
Current Challenges
FY23 Project Objectives
Identify instrument package useful for mesocosm CO2 and water quality monitoring
Purchase, deploy, maintain, and iterate
Deliverables
Recent Successes
Data, images, schematics etc.
Get vendor quotes for improved CO2 sensors – Q1
Select (in coordination with Task 2b) and order CO2 sensors – Q2
Deploy CO2 sensors and water quality sensors – Q3/Q4
Work up dataset and report out – Q4
Ground-truthing sensor capabilities in a controlled setting: does our selected system do what we need?
Developing SOPs for deployment/maintenance
Developing a ML data analysis pipeline
Collecting a potentially publishable dataset (water quality as a proxy for CO2)
Working out sensor logistics – wiring/logging/etc
Once sensors are received, will need to install in coordination with Task 2b renovations
Sensors ordered! – delivered late March / early April
Inventory of available water quality sensors completed
Maintenance tentatively sorted out - Bowe
Developing an approach to link CO2 sensors ($$$) to water quality sensors (in hand)
Flowchart of project tasks, how they relate, and who is responsible